## Informed Lightning Protection
Project | 9dc174ca-661f-448c-84db-a9eb010aa588
CreatedBy | SSEN Master SSEN Master
DateCreated | 05/02/2019 16:13:43 | 02/04/2019 13:12:12
RevisionId | 23164 | 23436
MajorVersion | 1
MinorVersion | 3 | 4
Name | Informed Lightning Protection
ShortName | Informed Lightning Protection
Reference | NIA_SSEN_0035
Sector | ElectricityDistribution
StartDate | 01/03/2019 00:00:00
Duration | 48
Logo
BackgroundImage
Budget | 521000.0000
ProjectContact | Joe McNeil
ProjectEmail | fnp.pmo@sse.com
ResearchAreaIds | 3646653d-d4cd-e711-93f1-001517891cc5,3846653d-d4cd-e711-93f1-001517891cc5
ProjectUpdate
ChangeControl
FundingMechanism | Network Innovation Allowance
Introduction | Lightning strikes are known to cause a significant number of supply interruptions to our customers.&nbsp; In our Scottish Network, lighting strikes are the second highest cause of customer interruptions and minutes lost and in our Southern Network it is the fifth highest cause.&nbsp; Therefore, there is a need to reduce the impact that lighting related faults have on our customers.
Benefits
Problems | Lightning strikes are known to cause a significant number of supply interruptions to our customers.&nbsp; In our Scottish Network, lighting strikes are the second highest cause of customer interruptions and minutes lost and in our Southern Network it is the fifth highest cause.&nbsp; Therefore, there is a need to reduce the impact that lighting related faults have on our customers.<br /><br />One method of reducing lightning related faults is to install surge arresters.&nbsp; Present practice of installing surge arresters involves identifying circuits that historically experience large numbers of lighting related faults and applying blanket coverage of surge arresters on these circuits i.e. installing surge arresters on every third pole.&nbsp; However, many of our circuits extend long distances i.e. over 30km in length, which means thousands of surge arresters would be necessary for blanket protection.&nbsp; Not only is this expensive but it may be ineffective as lightning may only strike in small hot spots around the network.&nbsp; There is a need to identify where lightning hot spot locations occur and to understand the impacts of supply interruptions to our customers in these areas.&nbsp; This will help inform us on where to install surge arresters for maximum prevention of supply interruptions at minimum cost.&nbsp; To do this, we plan on combining multiple data sets e.g. lightning strike location data, ground resistance data, etc. and perform advanced data analytics to identify key locations for surge arresters to be installed.<br /><br />Our surge arresters are designed to withstand multiple lightning strikes and operate for about 12 years.&nbsp; However, many of these surge arresters can fail prematurely without ever experiencing or protecting against a lightning strike.&nbsp; So, rather than preventing supply interruptions, they can cause them.&nbsp; Furthermore, it is difficult to diagnose when one of these types of surge arresters has failed as often there are no visible signs of failure.&nbsp; This increases the time taken to identify and fix/replace the failed arrester, which means customers are potentially off supply for long periods of time or money is spent on expensive and carbon intensive diesel generators.&nbsp; There is a need to perform an in-depth trial of surge arresters with the ability to disconnect, which are designed to sacrifice themselves in the event of a lightning strike or premature failure.&nbsp; This will prevent supply interruptions occurring and make it easier for field staff to identify which surge arresters have failed (as the earth lead will have disconnected), so they can be more easily replaced.
Methods | Lightning Development Phases<br /><br />Phase 1a &ndash; Data Analytics Pre-Execution Phase.&nbsp; This phase involves preparation work to ensure the execution phase runs smoothly.&nbsp; Specifically, it involves the following tasks<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Define model success criteria<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Create model requirements specification<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Provide Data Analytics Team (DAT) with necessary data sources required to implement functional requirements<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Perform data compatibility testing<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Perform GDPR &amp; Security Assessment<br /><br />Phase 1b&ndash; Data Analytics Execution Phase.&nbsp; This is the actual &lsquo;analytical&rsquo; phase of the project, where a geospatial model is created to analyse various data inputs including:<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Lightning strike location data<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Customer number data<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Lightning IIS fault data<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Lightning Opex data<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Ground resistivity data<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; GIS asset data<br /><br />The objective of this phase is to identify high risk areas or &lsquo;hot spots&rsquo; where lightning protection should be installed.&nbsp; Both probability of strike and impact of strike will be utilised in the identification process i.e. high-risk sites will not only be susceptible to lightning strikes, but also contain a significant number of customers that are at risk of experiencing a lightning related outage.&nbsp;<br /><br />Phase 2 &ndash; Internal review of high risk sites: Once the high-risk sites have been identified, the specific sections of these circuits, identified for lightning protection, will be reviewed internally.&nbsp; This is to confirm they are suitable for protection e.g. confirm no investment is planned to take place that may address the lightning issue and to sense check that these are suitable for protection.<br /><br />Phase 3 &ndash; Lightning protection procurement: Surge arresters will be installed on the network i.e. surge arresters with earth lead disconnects.&nbsp; Surge arresters with earth leads that disconnect can prevent outages from occurring if the surge arrester unit faults.&nbsp; This is a common occurrence that can lead to an unplanned outage.<br /><br />Phase 4 &ndash; Installation: Lightning protection equipment will be installed in locations defined by the data analytics model.&nbsp; This will be contracted to increase external spend with SSEN supervision.<br /><br />Phase 5 &ndash; Monitoring &amp; Analysing: Weekly monitoring of IIS and strike data will take place, possibly moving to fortnightly or monthly depending on the value of frequent monitoring.&nbsp; Annual reporting will take place detailing lightning strike frequency and IIS costs on selected locations.&nbsp; Any learning will also be detailed here e.g. faulty equipment, issues, etc.<br /><br />Phase 6 &ndash; Reporting, Dissemination &amp; Closedown: learnings derived from the project will be used to create new policy and processes on lighting protection investment methodology.&nbsp; Any learning will be shared with the wider DNO community. | Lightning Development Phases<br /><br />Phase 1a &ndash; Data Analytics Pre-Execution Phase.&nbsp; This phase involves preparation work to ensure the execution phase runs smoothly.&nbsp; Specifically, it involves the following tasks<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Define model success criteria<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Create model requirements specification<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Provide Data Analytics Team (DAT) with necessary data sources required to implement functional requirements<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Perform data compatibility testing<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Perform GDPR &amp; Security Assessment<br /><br />Phase 1b&ndash; Data Analytics Execution Phase.&nbsp; This is the actual &lsquo;analytical&rsquo; phase of the project, where a geospatial model is created to analyse various data inputs including:<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Lightning strike location data<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Customer number data<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Lightning IIS fault data<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Lightning Opex data<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Ground resistivity data<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; GIS asset data<br /><br />The objective of this phase is to identify high risk areas or &lsquo;hot spots&rsquo; where lightning protection should be installed.&nbsp; Both probability of strike and impact of strike will be utilised in the identification process i.e. high-risk sites will not only be susceptible to lightning strikes, but also contain a significant number of customers that are at risk of experiencing a lightning related outage.&nbsp;<br /><br />Phase 2 &ndash; Internal review of high risk sites: Once the high-risk sites have been identified, the specific sections of these circuits, identified for lightning protection, will be reviewed internally.&nbsp; This is to confirm they are suitable for protection e.g. confirm no investment is planned to take place that may address the lightning issue and to sense check that these are suitable for protection.<br /><br />Phase 3 &ndash; Lightning protection procurement: Surge arresters will be installed on the network i.e. surge arresters with earth lead disconnects.&nbsp; Surge arresters with earth leads that disconnect can prevent outages from occurring if the surge arrester unit faults.&nbsp; This is a common occurrence that can lead to an unplanned outage.We will also consider the installation of novel surge arresters, such as those with drop out mounts, that are able to prevent the need for unplanned outages after the arrester is spent or reaches end of life.<br />&nbsp;<br /><br />Phase 4 &ndash; Installation: Lightning protection equipment will be installed in locations defined by the data analytics model.<br /><br />Phase 5 &ndash; Monitoring &amp; Analysing: Weekly monitoring of IIS and strike data will take place, possibly moving to fortnightly or monthly depending on the value of frequent monitoring.&nbsp; Annual reporting will take place detailing lightning strike frequency and IIS costs on selected locations.&nbsp; Any learning will also be detailed here e.g. faulty equipment, issues, etc.<br /><br />Phase 6 &ndash; Reporting, Dissemination &amp; Closedown: learnings derived from the project will be used to create new policy and processes on lighting protection investment methodology.&nbsp; Any learning will be shared with the wider DNO community.
Scope | &middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Only 11kV and 33kV circuits will be protected.<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Protection will target lightning related faults only.<br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Development of the lightning model is for analytical purposes only.<br /> Results will be reviewed over a four-year period, but this time scale can be shortened if objectives are met earlier.
Objectives | 1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Develop a &lsquo;point in time&rsquo; lightning analysis tool that can be used to locate lightning protection equipment in the most optimal way i.e. integrate various data sets and update visual display as described in phase 1a and 1b above.<br /><br />2)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Install lightning protection equipment in &lsquo;optimal&rsquo; locations provided by the lightning analysis tool.<br /><br />3)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Monitor and analyse fault data to confirm effectiveness of lightning protection.<br /><br />4)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Update internal policies and procedures if the project is successful.<br /><br />5)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Share learnings with wider audience.
SuccessCriteria | The project will be a success if:<br /><br />1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; A point in time analytical tool is sufficiently developed so that it can integrate the different data sources described in phase 1b and perform advanced analytics, so that it can be used for the purpose of deciding where to place lightning protection equipment down to the nearest pole.<br /><br />2)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; We install lightning protection equipment safely, on time and within budget.<br /><br />3)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; We prove the effectiveness of this methodology for protecting against lightning related faults from a cost and fault reduction point of view.
TRLStart | TRL 1
TRLCompletion | TRL 8
ProjectPartners | N/A
NewLearning | The findings from this project will:<br /><br />1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Discover if this methodology is effective for protecting against lightning faults.<br /><br />2)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Determine the effectiveness of surge arresters with disconnects on the network.<br /><br />3)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Advance the geo-spatial analytical capabilities of digital tools in the field of lightning protection.
ProjectScale | This project is focusing primarily on lightning analysis, of which limited data sets are available and as such should not be overly complex.&nbsp; It is expected that the modelling phase will take about 3 months in total to complete.<br /><br />Investment in lightning protection equipment will not be large as we are trialling new kit to determine its effectiveness on the network and funds are limited.<br /><br />The length of the project is expected to be about 4 years.&nbsp; This is due to the randomness associated with lighting.&nbsp; It may therefore take some time before we can form conclusions on the success of the project.
GeographicalArea | This project will be located across both our Scottish &amp; Southern regions.
RIIOSettlement | None.&nbsp; No allowance was provided for additional protection against lightning.
ProjectExpenditure | &pound;521k
PEA2ALearning | Yes
PEA2ASharing | 1)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Adopting the methodology used in this project to analyse lightning risk on their networks.<br /><br />2)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Using the learning generated by this project to create a similar digital application.<br /><br />3)&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Installing new more cost-effective surge arresters that have been trialled in the UK as a result of this project.
PEA2AChallenge | This project addresses the &lsquo;reliability&rsquo; challenge.&nbsp; It aims to reduce both customer interruptions (Cis) and customer minutes lost (CMLs) by reducing the number of lightning faults on our network.
PEA2BIPR | Yes
PEA2BDissemination
PEA2BPotentialConstraints
PEA2BValueForMoney
PEA2CBenefits | Yes
PEA2CSaving | &pound;210k per annum (depending on how many circuits are protected).
PEA2CCalculation | Assumptions<br /><br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Incentive Interruption Scheme (IIS) costs are used to demonstrate savings.&nbsp; These are the costs Ofgem use to reflect the value of customer minutes lost and customer interruptions from a monetary point of view.&nbsp; No capital savings are expected to be realised by this project.&nbsp; Some operational savings from reduced use of diesel generators are expected, but have not been included here.<br /><br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Costs and savings are spread over a 12-year period, which is the average expected life span of lightning protection equipment (surge arresters).<br /><br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Project costs i.e. model development, project management time, etc. have been excluded in order to calculate the benefits of this in a business as usual environment.<br /><br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; This project is assumed successful and as a result 30 circuits at high risk of experiencing lightning faults will be protected.<br /><br />&middot;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp;&nbsp; Optimal location of lightning protection will reduce IIS costs by 50% per circuit.<br /><br />&nbsp;Base cost<br /><br />Scenario: 30 circuits with no lightning protection.<br /><br />30 circuits with high risk of experiencing lightning faults @&pound;25k average annual lightning related IIS costs per circuit = &pound;750k IIS cost per annum and &pound;9m over 12 years.<br /><br />&nbsp;Method cost<br /><br />Scenario: 30 circuits with &lsquo;optimal&rsquo; lightning protection.<br /><br />Lightning protection equipment procurement &amp; installation: 30 circuits @ &pound;50k per circuit = &pound;1.5m over 12 years.<br /><br />50% reduction in lightning faults due to protection = &pound;4.5m over 12 years<br /><br />&nbsp;Total method cost = &pound;4.5m+&pound;1.5m = &pound;6m over 12 years<br /><br />Base cost of &pound;9m &ndash; Method cost of &pound;6m = &pound;3m saving over 12 years or &pound;250k per annum
PEA2CReplication | This method can be rolled out to all GB DNO regions.&nbsp; The frequency of lightning strikes and lightning related faults will determine the possible savings.&nbsp;<br /><br />Assuming savings are similar across all 8 DNO regions in the UK:<br /><br />&pound;3m x 8 = &pound;24m GB savings over 12 years or &pound;2m per annum (average).
PEA2CCosts | Assuming costs are similar for all 8 DNO regions in the UK:<br /><br />&pound;6m x 8 = &pound;48m costs over 12 years or &pound;4m per annum (average).
PEA2DDuplication | Yes
PEA2DDemo | Presently there is no analytical tool that is able to perform geospatial analytical capabilities while integrating several data sources in order to determine optimal location of lightning protection equipment.&nbsp; This project builds on the learnings from an existing technology (Lightning tracker app) that was created as part of an NIA project and thus advances our capabilities and understanding in the field of lightning.
PEA2DDuplicationReason | N/A
ApprovedBySeniorStaff | True
Status | Live
DurationInYears | 4
DurationInMonths | 0
EndDate | 01/03/2023 00:00:00
DurationString | 4 years and 0 months
BudgetString | &pound;521,000.00
OtherSectorsDisplayList | Electricity Distribution
AllSectorsDisplayList | Electricity Distribution
FundingLicenseesDisplayList | Scottish Hydro Electric Power Distribution and Southern Electric Power Distribution
NetworkOperatorsDisplayList | Scottish and Southern Electricity Networks
PEA1sDisplayList
RequiresOfGemApproval | False
RequiresOfGemApprovalDisplay | NO (as indicated by the responses to the PEA)
TechnologiesDisplayList | Health and Safety and Network Monitoring
ResearchAreaDisplayList | ED - Network improvements and system operability, ED - Safety and health and environment